## Status Report Page 1
Status Report (Page 1) | [7 empty] | List Data - Do Not Edit
| Project Name: | CSU ATM | [5 empty] | Completed | 1
| Team Members: | Ankush, Brandon, Justin, Roshin, Suhev | [5 empty] | Discarded | 2
| Date: | 2021-11-05 | Cycle: | 1 |  |  |  | Collaboration | 3
Adversarial
In Review
Unstarted
| Cycle Intent: | set up the project plan. Delegate work for all members
|  |  | Planned |  |  | Actual
# | User Story |  | Total planned hours | Planned hours this cycle | Status | Total hours
1 | As a user, I can withdraw my money |  | 10 | 3 | Collaboration | 3
2 | As a user, I can check my bank balance |  | 10 | 3 | Collaboration | 3
3 | As a user, I can transfer money to any other accound |  | 10 | 3 | In Review | 3
4
5
|  |  | Planned Total | 30 | 9 | Actual Total | 9

## Ankush Timesheet
CPSC4175 Status Report - Member Timesheet
Project Name: |  | CSU ATM
Member: |  | Ankush
Week Ending: |  | INSERT DATE HERE
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Worked on thigamajig. Integrated the sprocket with the cog. Developed a test plan for the widget.
Date: | 2011-12-25 | Result: | Thigamajig completed and ready for unit testing. Sprocket and cog integration 65% complete.
Hours Worked: | ? | Problems encountered: | Sprocket and cog don't fit together correctly. A kotter pin might be required to hold the cog in place.
Day: | Wednesday | Task(s) performed:
Date: | 2011-12-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2011-12-27 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2011-12-28 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2011-12-29 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2011-12-30 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2011-12-31 | Result:
Hours Worked: | ? | Problems encountered:

## Brandon Timesheet
CPSC4175 Status Report - Member Timesheet
Project Name: |  | CSU ATM
Member: |  | Brandon
Week Ending: |  | INSERT DATE HERE
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Worked on thigamajig. Integrated the sprocket with the cog. Developed a test plan for the widget.
Date: | 2011-12-25 | Result: | Thigamajig completed and ready for unit testing. Sprocket and cog integration 65% complete.
Hours Worked: | ? | Problems encountered: | Sprocket and cog don't fit together correctly. A kotter pin might be required to hold the cog in place.
Day: | Wednesday | Task(s) performed:
Date: | 2011-12-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2011-12-27 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2011-12-28 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2011-12-29 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2011-12-30 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2011-12-31 | Result:
Hours Worked: | ? | Problems encountered:

## Justin Timesheet
CPSC4175 Status Report - Member Timesheet
Project Name: |  | CSU ATM
Member: |  | Justin
Week Ending: |  | INSERT DATE HERE
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Worked on thigamajig. Integrated the sprocket with the cog. Developed a test plan for the widget.
Date: | 2011-12-25 | Result: | Thigamajig completed and ready for unit testing. Sprocket and cog integration 65% complete.
Hours Worked: | ? | Problems encountered: | Sprocket and cog don't fit together correctly. A kotter pin might be required to hold the cog in place.
Day: | Wednesday | Task(s) performed:
Date: | 2011-12-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2011-12-27 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2011-12-28 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2011-12-29 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2011-12-30 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2011-12-31 | Result:
Hours Worked: | ? | Problems encountered:

## Roshin Timesheet
CPSC4175 Status Report - Member Timesheet
Project Name: |  | CSU ATM
Member: |  | Roshin
Week Ending: |  | INSERT DATE HERE
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Worked on thigamajig. Integrated the sprocket with the cog. Developed a test plan for the widget.
Date: | 2011-12-25 | Result: | Thigamajig completed and ready for unit testing. Sprocket and cog integration 65% complete.
Hours Worked: | ? | Problems encountered: | Sprocket and cog don't fit together correctly. A kotter pin might be required to hold the cog in place.
Day: | Wednesday | Task(s) performed:
Date: | 2011-12-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2011-12-27 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2011-12-28 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2011-12-29 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2011-12-30 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2011-12-31 | Result:
Hours Worked: | ? | Problems encountered:

## Suhev Timesheet
CPSC4175 Status Report - Member Timesheet
Project Name: |  | CSU ATM
Member: |  | Suhev
Week Ending: |  | INSERT DATE HERE
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | started Django project, went through a quick tutorial
Date: | 2021-02-11 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2011-12-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed: | Used sqlite to build a database
Date: | 2021-04-11 | Result:
Hours Worked: | 3 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2011-12-28 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2011-12-29 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2011-12-30 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2011-12-31 | Result:
Hours Worked: | ? | Problems encountered: